## Introduction
MVOD Initiative Tracker
As described under the Communications Strategy, the Mackenzie Valley Operational Dialogue (MVOD) tracks progress on internal and external resource management iniatives throughout the Mackenzie Valley. The Organizing Committee updates this document before upcoming workshops and touchstone meetings.
This document was last updated: August 2023.
There are 2 tabs in this tracking document:
  • Light Work Plans - This tab tracks updates on the current Light Work Plans.
  • NWT Audit Recommendation - This tab tracks outstanding and current MVOD-related recommendations from the NWT Environmental Audit.

## Light Work Plans
Light Work Plans (LWPs)
Light Work Plans | Goal | Current Status | Next Steps | Contact
1. Administrative Challenges | Identify administrative and/or business challenges within the application stream for small-scale exploration, and develop solutions to improve them. | Ongoing – Technical experts have identified 5 administrative challenges, work is underway to address them | • Present on discussions and actions to date at MVOD+ workshop | Benji Straker (GNWT, Benji_Straker@gov.nt.ca); Kathy Racher (MVLWB, kracher@mvlwb.com)
2. Education and Outreach | Develop plain language information material to describe the components of the resource management regime, which could include information sheets on general grassroots/small-scale exploration and specific minerals, training for communities/decision-makers, etc. Information will be made publically available whenever possible. | Ongoing – LWP 2 is being refocused, suggestions are being developed. Information sheets on specific critical minerals are being developed and will be shared. | • Suggestions will be shared at the upcoming MVOD+ workshop and feedback will be sought | Benji Straker (GNWT, Benji_Straker@gov.nt.ca); Kathy Racher (MVLWB, kracher@mvlwb.com); Rebecca Chouinard (CIRNAC, rebecca.chouinard@rcaanc-cirnac.gc.ca)
3. ORS Analytics | Develop a tracking system on the ORS to track/display timelines for applications (LUPs/WLs/etc.) to help inform discussions. Ideally this information could publicly depict statistics/analytics each month (quantitative). Where timelines are extended, projects referred to EA, or other issues arise; a brief description of the situation/issue (qualitative) could be included. Upgrade ORS to provide for automated application submissions (application forms/management plans/etc.) | Ongoing – Premiminary analytics are published, information is being populated | • Develop further analytics to be added | Kathy Racher (MVLWB, kracher@mvlwb.com)
4. Communications Strategy | Draft a communication plan to clarify steps all parties will take to encourage “a no-surprises dialogue-first” approach when there are new developments, questions, issues/challenges pertaining to specific projects, policies, guidelines, approaches, etc. Develop system to track list of topics that have been raised at MVOD sessions, but are not currently part of MVOD’s near-term work planning or fall outside of the scope of MVOD and identify topics where cross-communication would be beneficial (to feed into other processes/groups, and to receive updates on these initiatives). Develop plan to communicate/post this information publicly, and to update it regularly. | Finalized - Communication strategy has been posted, and tracking initiative will be updated before workshops. | • N/A | Rebecca Chouinard (CIRNAC, rebecca.chouinard@rcaanc-cirnac.gc.ca)

## NWT Audit Recommendations
Outstanding Recommendations from 2015 NWT Environmental Audit Pertaining to Regulatory Activities
Lead | Topic | Recommendation | Status
GNWT | Securities | GNWT Department of Lands (Lands) should develop policy documents outlining its approach to and timeline for establishing a structured approach to securities management within the NWT. | Outstanding
GNWT | Consultation and Engagement | The GNWT should develop a clear policy and program to address and communicate its responsibilities for consultation and public engagement. | Outstanding
CIRNAC | Consultation and Engagement | (CIRNAC) should make the development of regulations on consultation a priority to add further clarity and certainty to the regulatory process. | Outstanding
2020 NWT Environmental Audit Recommendations That Can be Addressed Through MVOD
Lead | Topic | Recommendation | Status
GNWT & CIRNAC | Communication and Transparency | 1-2: The GNWT and CIRNAC establish a process for parties to meet on a regular basis and discuss implementation opportunities and challenges with respect to the integrated system of land and water management in the Mackenzie Valley. At times, this process will need to include IGOs and industry as appropriate. We further recommend CIRNAC ensure a record of findings, actions, and outcomes are published to ensure transparency and to facilitate monitoring and auditing of progress. | Ongoing - Being addressed through LWP 4
GNWT | Communication and Transparency | 1-4: The GNWT refresh its NWT Mineral Development Strategy with the express goal of demonstrating unity in messaging and approach. Opening statements from the Premier, the Minister, and the Chamber of Mines should be enhanced by messaging from IGOs. | Not started
GNWT | Regulatory Improvement | 1-5: The GNWT include a section in the Mineral Development Strategy describing aspects of the regulatory system that are important to industry such as clarity on timelines and regulatory improvements that are felt to be limiting mineral development. This may require engagement with a range of regulators including the LWBs to ensure the accuracy of any messages or conclusions. | Ongoing - being addressed through LWP 1
LWBs | Regulatory Improvement | 1-7: That the LWBs regularly meet with key client groups outside of specific regulatory processes to discuss opportunities and challenges with the goal of continuing to improve the regulatory system. We further recommend the LWBs use the information from these engagement sessions to inform priorities and workplans. | Ongoing - Being addressed through LWP 1 and 2
GNWT & LWBs | Regulatory Improvement | 1-8: The LWBs and the GNWT develop a standardized mineral exploration permitting bundle, in consultation with affected parties, similar to what the MVLWB has already done for municipal water licences. | Not started
GNWT & CIRNAC | Consultation and Engagement | 1-10: The GNWT and the federal departments with responsibility for engagement and consultation under the MVRMA work with their respective clients to review and improve engagement strategies. | Not started
LWBs | Consultation and Engagement | 1-11 The MVLWB re-examine its engagement process and enhance the process where appropriate to better detect emerging public concerns and to adapt their plan for engagement as required. | Not started
GNWT, LWBs, & CIRNAC | Consultation and Engagement | 1-16 The LWBs seek to develop a participant funding program, funded by the federal and territorial governments, to support regulatory decisions within its jurisdiction. The funding would provide capacity support to Indigenous parties requiring assistance to participate in the regulatory process, as well as technical support. | Not started
GNWT & CIRNAC | Regulatory Improvement | 1-19: The GNWT develop and publish an overall project inspection scheme to assist regulators, the public, and permit holders in tracking of ‘unacceptable’ items from previous inspections all the way to their satisfactory conclusion and inspector sign-off. Furthermore, improvements could be made in the consistency of information collected to ensure future inspectors, the proponent, and regulators appreciate the context of an inspection. We encourage the GNWT to work with their Federal counterparts on this initiative, including CIRNAC and the Canada Energy Regulator. | Not started